## Sayfa1
Multimodal-RAG-Based-Product-Recommendation-System |  | WEEKS
Procedural Steps | Current State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Updated SRS, SDD, Work Plan | Completed | 1: 1; 2: 2; 3: 3
Test Plan Document | In Progress | 2: 2; 3: 3; 4: 4
Software Development Process | In Progress |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Demo Presentation | In Progress |  | 4 8: 8
Updated Test Plan Document | In Progress |  | 4 11: 11 | 12 | 13
User Manual | In Progress | [11 empty] | 12 | 13
Project Poster | In Progress | [13 empty] | 14
Project Report | In Progress | [13 empty] | 14
Updated Project Webpage | In Progress | [14 empty] | 15
Demo Video | In Progress | [14 empty] | 15
Presentation | In Progress | [15 empty] | 15