## Sayfa1
Multimodal-RAG-Based-Product-Recommendation-System |  | WEEKS
|  | 30 September - 6 October | 7 October - 13 October | 14 October - 20 October | 21 October - 27 October | 28 October - 3 November | 4 November - 10 November | 11 November - 17 November | 18 November - 24 November | 25 November - 1 December | 2 December - 8 December | 9 December - 15 December | 16 December - 22 December | 23 December - 29 December | 30 December - 5 January | 6 January - 12 January
Procedural Steps | Current State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Team Setup | Completed | bar: 1
Project Proposal Form | Completed | 1: 1; 2: 2
Project Selection Form | Completed | 1: 1; 2: 2
GitHub Repository | Completed | 3: 3
Project Work Plan | Completed | 3: 3; 4: 4
Literature Review | Completed | 4: 4; 5: 5; 6: 6
Software Requirements Specification | Completed | 6: 6; 7: 7; 8: 8; 9: 9; 10: 10
Project Webpage | Completed | 10: 10; 11: 11
Software Design Description | Completed | 10: 10; 11: 11; 12: 12; 13: 13
Project Report / Project Tracking Form | Completed | 13: 13; 14: 14; 15: 15
Presentation | Completed | 15: 15